## RFP Project Plan
RFP Title
Milestone description | Assigned to | Progress | Start Date | Days | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T
Initial discussion: confirm business case, budget approval, stakeholders, requirements. | Procurement | 100% | 2025-07-15 | bar: Days to T
Kick-off meeting: discuss RFP objective, requirements, timelines, roles/responsibilities. | Procurement / Business | 100% | 2025-07-15 | bar: Days to T
Vendor list: research and compile list of potential vendors. | Procurement | 50% | 2025-07-16 | Days: 10
RFP documents: prepare RFP documents with project scope, deliverables, expectations, timeline, and evaluation criteria. | Procurement | 0% | 2025-07-28 | Days: 5
RFP process: send out RFP, answer vendors questions and compile proposals. | Procurement | 0% | 2025-08-05 | bar: Days; M
Demos: schedule if needed | Procurement | 0% | 2025-08-06 | Days: 15
Site visits: schedule if needed | Procurement | bar: T
Vendor evaluation: score and evaluate proposals, shortlist a few vendors | Business | 0% | 2025-08-28 | bar: Days; W to W
Negotiations: negotiate price, SLAs and timelines. | Procurement | 0% | 2025-08-29 | Days: 2
Vendor selection: choose the final vendor(s) based on best value, timeline, and alignment with project goals. | Business | 0% | 2025-09-08 | Days: 5
Contract signature: work with legal teams to finalize contract details with the chosen vendor(s). | Legal / Procurement | 0% | 2025-09-15 | Days: 5

## Vendor List
RFP Title
Company | Incumbent | Contact name | Phone | Email | Comments | NDA | Accept RFP | Proposal Received | Demo/POC
Vendor 1 | Yes
Vendor 2 | Yes
Vendor 3 | No